Standard Operating Procedure:

Project Closure

| Supersedes: | Project Closure SOP (UoB-CLO-SOP-001, v2.0) |
| --- | --- |
| Last reviewed: | Jun-2026 |
| Next review in: | 2029, Quarter 2 (Apr-Jun) |

Access the Clinical Research e-Pathway for a roadmap to help navigate a complete project lifecycle.

Contents

Purpose	3

Scope	3

Implementation plan	3

Stakeholders	3

Background	3

Procedure	4

1.	Defining project closure	4

2.	Notifying end of project	4

3.	Early termination	5

4.	Abandoned projects prior to commencement	5

5.	Clinical research samples	5

6.	Data analysis	6

7.	Final report and publications	6

Summary report and public registers	6

8.	Information to participants at the end of a project	6

9.	Sponsor oversight	7

10.	Archiving	7

List of expected outputs	8

Related documents	9

References & frameworks	9

Abbreviations	10

Document contributors	11

Document history	12

Document version log	12

Document revision log	12

# Purpose

This standard operating procedure (SOP) describes the requirements relating to project closure. This includes notification for the end of project, early termination, and abandoned projects. It also outlines the requirements for the handling of clinical research samples at the end of the project and the final reports on research and publications, including reporting to public registries.

# Scope

This SOP applies to: (1) clinical research sponsored by the University of Birmingham (UoB); (2) clinical research sponsored by another institution, except to the extent that the SOP is inconsistent with any contract between UoB and that institution; and (3) clinical research approved by a UoB research ethics committee (REC) in circumstances where the REC requires that the clinical research conform with the UoB Principles of Good Clinical Practice (GCP) for Clinical Research (UoB-GCP-POL-001).

Where this SOP does not apply, the chief investigator (CI) of a clinical research project may at their discretion refer to it as a non-binding source of guidance.

Note: for clinical research approved by a UoB REC, there is no requirement for end of project notifications or registration on a publicly accessible database. However, there may be a requirement outside the UoB quality management system (QMS) to register the project e.g., required by a funder or publisher.

# Implementation plan

This SOP will be implemented directly after its effective date.

# Stakeholders

Note that where the UoB takes on the sponsor responsibility for project closure, the UoB will delegate majority of these duties to the chief investigator (CI) and/or to a clinical trials unit (CTU), who may delegate these duties further to their trial team(s). All delegation of duties will be documented (e.g. using either the CI declaration and/or the Clinical Trials Task Delegation Log (UoB-SPO-QCD-001).

- CI: the CI may delegate activities to members of their research team, although evidence of CI oversight and approval is still expected and may not be delegated where ‘no delegation allowed’ is indicated. The SOP will state where delegation is possible. For clinical research approved by a UoB REC, the role of CI may be termed the principal investigator, or the supervisor for postgraduate research students.

- Research Ethics, Governance and Integrity Team (REGI)

- UKCRC-registered UoB CTUs

# Background

For the purposes of this SOP, the terms ‘clinical research’ or ‘project’ will cover clinical trials of investigational medicinal products (CTIMPs), other interventional trials (e.g. surgical trials, device trials and non-CTIMP trials, and any other projects deemed to be ‘interventional’ by the sponsor), and clinical studies.

In accordance with the Medicines for Human Use (Clinical Trial) Regulations 2004 (as amended) and the Health Research Authority SOPs, written notification for project closure is to be given within 90 days of the global end of the project, or within 15 days if the project is terminated early.

Final analysis of the data and report writing is normally considered to occur after formal declaration of the project closure. A summary of the final research report must be sent to the REC and the competent authority (CA; the Medicines and Healthcare products Regulatory Agency (MHRA) in the UK for CTIMPs and clinical investigations of medical devices) within 12 months of the project closure. For CTIMPs, see also the International Council on Harmonisation (ICH) efficacy guidelines for Structure and Content of Clinical Study Reports (ICH E3).

Note: in accordance with Regulation 78(13) and (14) of the Human Medicines Regulations 2012 (as amended), holders of a UK marketing authorisation who sponsor a study involving use of their authorised medicinal product in the paediatric population are required to submit study results to the MHRA within 6 months of trial end.

# Procedure

Defining project closure

The CI (or delegate) will define the end of the project and document this in the protocol. It is expected to be defined in relation to the collection of all data required to answer the research questions in the protocol. Where a protocol requires follow-up monitoring and data collection to meet secondary or exploratory endpoints, it is expected that the end of project is the final data capture rather than the last participant visit.

Where there is a change to this definition, after approval for the project has been given, the CI (or delegate) will notify the appropriate review bodies by the submission of a modification. For further details see the Project Set-up SOP (UoB-SET-SOP-001).

The CI (or delegate) will include in the protocol, if required, a description of the plan for the provision of any additional care for the participants once their participation in the project has ended, where it differs from what is normally expected according to the medical condition of the participant.

Notifying end of project

The protocol and any other documents approved by the REC (and the CA for CTIMPs) should be reviewed regarding the use of tissue and data collected during the project, the provision of information to participants and dissemination of results. If any changes to these approved arrangements are required, it is expected that consideration will be made whether a modification to the project is required before submitting the end of project notification.

The CI (or delegate) will notify the relevant review bodies of the end of the project, as defined in the protocol, using the appropriate end of trial/study declaration process. The specific form and submission route will depend on how the project was originally submitted and approved. Guidance on the correct process is available via the Clinical Trials Toolkit. The relevant review bodies include those listed below

The REGI

The REC that gave a favourable opinion of the research. Notification to the REC will be in writing and within 90 days of project conclusion. Note: for non-CTIMPs, the REC reference number is required on the end of study declaration.

Where applicable:

The Confidentiality Advisory Group (CAG). If the project has an application with CAG, the CI (or delegate) will notify the Confidentiality Advice Team as soon as possible in writing and retain evidence of their written confirmation of receipt of the application closure notice in the study/trial master file (S/TMF).

For international projects: where the UK arm of a project ends in advance of the global end of the project, the CI (or delegate) is expected to notify the relevant bodies as above. Note: the form for declaring the end of the project should not be used in this case.

Any contracted storage facilities or licensed tissue banks holding clinical research samples for the project should be notified of the anticipated end of project at least 90 days in advance.

For CTIMPs, the CI (or delegate) will also notify the CA within 90 days of the global end of the trial via the appropriate End of Trial Declaration form.

For projects that have received approval from the Health Research Authority (HRA) but were not reviewed by an NHS REC, the CI (or delegate) will notify the HRA that the project has closed by email to approvals@hra.nhs.uk within 90 days and include the Integrated Research Application System (IRAS) ID and their contact information (phone and email) in the correspondence.

The CI (or delegate) will ensure that all other applicable organisations are notified of the end of project including NHS Research and Development (R&D) offices, funder, any participating study/trial locations and as defined in contractual agreements.

The CI (or delegate) will retain the end of project declaration, including confirmation of receipt from relevant bodies, e.g. the REC (and the CA for CTIMPs), with any related correspondence, and ensure it is filed in the S/TMF.

The CI (or delegate) will continue to submit the relevant safety updates and modifications to the relevant review bodies, e.g. the REC (and the CA for CTIMPs) for the ongoing project, regardless of whether their country is still active or not, until the global end of project notification is submitted.

Early termination

If a project is terminated prior to the specified criteria being met, for reasons such as slow recruitment, the CI (or delegate) will notify the appropriate review bodies (the REC and REGI and the CA for CTIMPs) as described in ‘Notifying End of Project’ immediately and at least within 15 days.

The CI (or delegate) will clearly explain the reasons for early termination, including how the decision was made and by whom.

Note: if the project ends earlier than expected, not on the grounds of safety, but for other reasons, such as faster recruitment than anticipated, this is not considered as an ‘early termination’.

A modification to the project can be submitted alongside a declaration of early termination where it is necessary to seek ethical review of related actions e.g. informing participants, continuity of care and follow-up outside the project.

Where follow-up actions must be taken for safety reasons, the CI (or delegate) will report these to the REC (and the CA for CTIMPs).

The CI (or delegate) will retain the end of project declaration, including confirmation of receipt from relevant bodies with any related correspondence, and ensure it is filed in the S/TMF.

Abandoned projects prior to commencement

The project is considered to have commenced when any of the procedures that are set out in the protocol, such as participant screening or consent, are initiated. For projects abandoned post-commencement for any reason the ‘Early Termination’ process described above will be followed.

Note: when a CTIMP with a clinical trial authorisation (CTA) is abandoned, the ‘Early Termination’ process described above will be followed.

The CI (or delegate) will notify the appropriate bodies, giving reasons for abandoning the project, and copy the REGI into relevant correspondence. See list below to the appropriate bodies that may be included.

REC

Submission of the standard form for declaring project conclusion or early termination is not required. If the project is abandoned and later proposed to restart, a new application must be submitted.

Local NHS R&D offices.

Funders.

Any contracted storage facilities or licensed biobanks holding clinical research samples for the project, as defined in contractual agreements.

Where a project has HRA approval and was not reviewed by an NHS REC, the CI (or delegate) will inform the HRA when the project has ended via email to approvals@hra.nhs.uk, including the IRAS ID and contact information (phone and email).

Clinical research samples

Upon project closure, the CI (or delegate) will ensure that any remaining clinical research samples are handled in line with the ethical approval obtained, the protocol and with the consent obtained from the participant regarding the future use, storage (in a licensed tissue bank where required) or destruction of their samples.  Also, following declaration of the end of study, ethical approval permits retention and use of samples only for purposes necessary to final data verification, quality control and preparation of the final report, unless further ethical approval and appropriate consent are in place.

If the remaining samples constitute ‘relevant material’ as defined by the Human Tissue Act, they must also be handled in accordance with the Human Tissue Act (2004). Where this is the case, the samples (in line with the ethical approval, protocol and consent obtained) must be either:

stored in a Human Tissue Authority (HTA) licensed tissue bank such as the Human Biomaterials Resource Centre (HBRC) or the Dentistry Research Tissue Bank.

transferred to another project with favourable ethical opinion from an NHS REC. Note: an application/modification must be submitted to an NHS REC to transfer the samples to the other project before favourable opinion of the existing project expires.

destroyed in accordance with the HTA Code of Practice and in line with local health and safety policies.

For further details, see the Laboratory Set-up and Management SOP (UoB-CRL-SOP-001) and Sample Management SOP (UoB-CRL-SOP-003).

Data analysis

The CI (or delegate) will commence final analysis of the data (following “lock” of the project database) and report writing after formal declaration of the project closure and in accordance with the protocol, project-specific data management plan and statistical analysis plan. See also the Data Management SOP (UoB-DMA-SOP-001) and Statistics SOP (UoB-STA-SOP-001).

Final report and publications

Note: in line with the UoB Code of Practice for Research (PDF - 459 KB), all researchers who publish a paper related to their trial or study are required to include a record of their scholarly works in the relevant University repository. Please see the current University repository, Pure (UoB login required), for further information about University’s research information management system

The CI (or delegate) will follow the reporting and publication procedures as detailed in the protocol (this includes cases of early termination).

For CTIMPs, the funder reference number or unique public registry number will be added to reports and publications.

For publications of randomised trials, the CI (or delegate) will also refer to the CONSORT (Consolidated Standards of Reporting Trials) statement guidelines, see the Statistics SOP (UoB-STA-SOP-001) for further details.

### Summary report and public registers

For reporting the summary of results, the CI (or delegate) will send a final report to the REC (and to the CA for CTIMPs where no public register is used; see point 21) within 12 months of the end of the project copying REGI into relevant correspondence. Where this is a global project, this is the end of the project in all participating countries, not just in the UK.

Note: there is no standard format for final reports, although, as a minimum, the CI (or delegate) is expected to supply the REC with information pertaining to whether the project achieved its objectives, the main findings, and arrangements for publication or dissemination of the research, including any feedback to participants.

At the time of reporting to the REC, the CI (or delegate) will ensure that the clinical research summary results are posted in the relevant registries (see the UoB Position Paper: Clinical Research Registration (Word – 309 KB)) within 12 months following the project closure. The exception to this is where either a deferral or waiver has been granted.

For CTIMPs, the CI (or delegate) will send a confirmation email to the HRA to study.registration@hra.nhs.uk  once the result-related information has been uploaded to the relevant public registry and will provide a link to the relevant website. See guidance HRA guidance on publishing trial results.

Note: CTIMPs involving locations specifically in EU countries must be registered in the EU Clinical Trials Register. This may involve obtaining an authorisation letter from the REGI and submitting the results to the European Medicine Agency Clinical Trials Information System (CTIS).

The CI (or delegate) will retain all correspondence pertaining to the summary reports including acknowledgements of receipt, which will be documented in the S/TMF.

If agreed, a copy of the summary report is expected to be sent to study/trial locations.

Information to participants at the end of a project

At the closure of the research project, the CI (or delegate) will be expected to fulfil commitments made to participants; see the Participant Engagement and Informed Consent SOP (UoB-PEI-SOP-001) for further details. For CTIMPs, participants and/or other relevant persons must be offered a summary of the trial results written in an easy-to-understand manner within 12 months of the end of the trial.

Examples of commitments to participants include:

direction to published or summary results

for CTIMPs, and other interventional trials, continued access by the participants to the IMP/intervention

Sponsor oversight

The CI (or delegate) will ensure that where external CTUs are involved in the management of the project, any formal communications (e.g. ‘Declaration of the end of a study’ form) is sent to the REGI for review prior to submitting to the REC/HRA (and the CA for CTIMPs).

When informed of a project’s closure, either through an annual report, a project closure report or otherwise, the REGI will monitor that relevant documentation is submitted to the REC (and CA for CTIMPs) in a timely fashion, and that the summary report is submitted within a year following submission to the REC (and the CA for CTIMPs). The REGI will liaise with the CI (or delegate) where timelines are not met, and report to the C-ROC where delays have been observed, and the actions taken by the REGI.

Archiving

Following the development of the summary report and subsequent distribution, the CI (or delegate) will archive the project. See also the Archiving SOP (UoB-ARC-SOP-001).

# List of expected outputs

Definition of the end of the project documented in the protocol and evidence of notification to the REC (and the CA for CTIMPs) of any changes made regarding the end of the project.

A description in the protocol of the plan for the provision of additional care to participants after the research has ended, should it differ from standard care.

Reporting and publication policy documented in the protocol.

For projects with an application with the CAG, evidence that the Confidentiality Advice Team has been notified and that confirmation of receipt of the application closure notice is filed in the S/TMF.

Documented evidence in the S/TMF of notification to REGI, the REC (and the CA for CTIMPs), as applicable, of project conclusion or early termination within required timelines (90 days for normal completion and 15 days for early termination from the defined end-of-project date), in accordance with applicable processes. Evidence should include confirmation of submission and receipt of the appropriate end-of-project notification.

Evidence that all other relevant organisations (e.g. NHS R&D offices, funders, participating locations) have been notified of the end of the project in accordance with contractual agreements.

Evidence that the REC (and the CA for CTIMPs), and the HRA where applicable, have been informed in cases where a project has been abandoned prior to commencement.

For projects terminated early, documented explanation of the rationale for termination and any follow-up actions taken.

Evidence that continued safety updates and modifications were submitted to the relevant review bodies for ongoing projects until the global end-of-project notification was submitted.

Evidence that any follow-up actions taken for safety reasons were notified to the REC (and the CA for CTIMPs) with proposed actions.

Evidence that remaining clinical research samples have been handled in accordance with the ethical approval, protocol requirements, participant consent and applicable legislation.

Evidence that reporting and publication procedures outlined in the protocol have been followed.

Evidence of research outputs following analysis, such as publications or reports.

Details of research outputs recorded in the relevant UoB research repository (i.e. Pure).

Where external CTUs are involved, evidence that formal communications (e.g. end-of-study declarations) were submitted to REGI for review prior to submission to the appropriate review bodies.

Evidence that a summary report has been provided to the REC (and to the CA for CTIMPs where applicable) within 12 months of the end-of-project date and that summary results have been posted on relevant public registries, unless a deferral or waiver has been granted.

For CTIMPs, evidence that participants and/or relevant persons have been offered an easy-to-understand summary of trial results within 12 months of the end of the trial.

Evidence that all correspondence relating to summary reports and registry submissions has been retained in the S/TMF.

Evidence of REGI oversight, including reporting to the C-ROC where delays in end-of-project notification or summary reporting have been identified.

# Related documents

UoB-ARC-SOP-001 Archiving

UoB-CRL-SOP-001 Laboratory Set-up and Management

UoB-CRL-SOP-003 Sample Management

UoB-DMA-SOP-001 Data Management

UoB-PEI-SOP-001 Participant Engagement and Informed Consent

UoB-SET-SOP-001 Project Set-up

UoB-SPO-QCD-001 Clinical Trials Task Delegation Log

UoB-STA-SOP-001 Statistics

Access to the full UoB QMS for clinical research is available via the CRCT website.

# References & frameworks

CONSORT (Consolidated Standards of Reporting Trials). (2025) Statement Guidelines. Available at https://www.consort-statement.org/ (Accessed 18-Feb-2026).

HRA. (2026) Deferrals. Available at: https://www.hra.nhs.uk/planning-and-improving-research/policies-standards-legislation/clinical-trials-investigational-medicinal-products-ctimps/clinical-trial-regulations-reform/guidance-on-changes-to-the-clinical-trials-regulations/research-transparency-requirements-for-clinical-trials/deferrals/ (Accessed: 02-Mar-2026.

HRA. (2025) Ending your project. Available at: http://www.hra.nhs.uk/approvals-amendments/managing-your-approval/ending-your-project (Accessed: 18-Feb-2026).

HRA. (2026) Publishing trial results. Available at: https://www.hra.nhs.uk/planning-and-improving-research/policies-standards-legislation/clinical-trials-investigational-medicinal-products-ctimps/clinical-trial-regulations-reform/guidance-on-changes-to-the-clinical-trials-regulations/research-transparency-requirements-for-clinical-trials/publishing-trial-results/ (Accessed: 02-Mar-2026).

HRA. (2026) Waivers. Available at: https://www.hra.nhs.uk/planning-and-improving-research/policies-standards-legislation/clinical-trials-investigational-medicinal-products-ctimps/clinical-trial-regulations-reform/guidance-on-changes-to-the-clinical-trials-regulations/research-transparency-requirements-for-clinical-trials/waivers/ (Accessed: 02-Mar-2026).

ICH (1996) E3 Guidelines: Structure and Content of Clinical Study Reports. Available at: https://www.ich.org/page/efficacy-guidelines (Accessed: 18-Feb-2026).

MHRA. (2025) Clinical trials for medicines: manage your authorisation, report safety issues. Available at:https://www.gov.uk/guidance/clinical-trials-for-medicines-manage-your-authorisation-report-safety-issues (Accessed: 18-Feb-2026).

MHRA. (2026) Clinical trials for medicines: apply for authorisation in the UK. Available at: https://www.gov.uk/guidance/clinical-trials-for-medicines-apply-for-authorisation-in-the-uk (Accessed: 18-Feb-2026).

NIHR. (2024) Clinical Trials Toolkit. Available at: https://www.ct-toolkit.ac.uk (Accessed: 18-Feb-2026).

UK Legislation. (2004) Human Tissue Act. Available at: http://www.legislation.gov.uk/ukpga/2004/30/contents (Accessed: 18-Feb-2026).

UK Legislation. (2004) The Medicines for Human Use (Clinical Trials) Regulations (as amended). Available at: https://www.legislation.gov.uk/uksi/2004/1031/contents (Accessed: 18-Feb-2026).

UK Legislation. (2012) The Human Medicines Regulations 2012 (as amended). Available at: https://www.legislation.gov.uk/uksi/2012/1916/contents (Accessed: 02-Mar-2026).

UoB (no date) Code of Practice for Research. Available at: https://www.birmingham.ac.uk/documents/university/legal/research.pdf (Accessed: 26 February 2026)

UoB. (no date) Human Biomaterials Resource Centre (HBRC) Available at: https://www.birmingham.ac.uk/facilities/hbrc/index.aspx (Accessed: 18-Feb-2026).

UoB. (no date) Pure Research Information System Available at: https://bham.sharepoint.com/sites/rssd/SitePages/pure.aspx (Accessed: 18-Feb-2026).

UoB. (2025) Position Paper: Clinical Research Registration. Available at: https://www.birmingham.ac.uk/documents/college-mds/crct/uob-position-papers/uob-position-paper-clinical-research-registration.docx (Accessed: 27-Feb-2026).

# Abbreviations

| CA | Competent authority |
| --- | --- |
| CAG | Confidentiality Advisory Group |
| CI | Chief investigator |
| CTA | Clinical trial authorisation |
| CTIMP | Clinical trial of an investigational medicinal product(s) |
| CTIS | Clinical Trials Information System |
| CTU | Clinical trials unit |
| C-ROC | Clinical research Oversight Committee |
| GCP | Good Clinical Practice |
| HRA | Health Research Authority |
| HTA | Human Tissue Authority |
| ICH | International Council on Harmonisation |
| IRAS | Integrated Research Application System |
| MHRA | Medicine and Healthcare products Regulatory Agency |
| QMS | Quality management system |
| R&D | Research and Development |
| REC | Research ethics committee |
| REGI | Research Ethics, Governance and Integrity Team |
| SOP | Standard operating procedure |
| S/TMF | Study/trial master file |
| UoB | University of Birmingham |

See also Glossary of Terms for a full list of abbreviations and definitions.

# Document contributors

Author(s)

Enayet Amin (Senior Quality Assurance Officer)

Reviewer(s)

Version by – Clinical Research Compliance Team (CRCT) Research Ethics, Governance & Integrity Team (REGI) University of Birmingham Clinical Trials Units (UoB CTUs) Clinical Research Oversight Committee (C-ROC) Human Tissue Oversight Committee (HTOC) Any other stakeholders (see stakeholders above) Revisions by – CRCT (see document revision log below)

Authoriser(s)

Jamie Douglas-Pugh (Clinical Research Compliance Manager / QMS Manager) Colin Watts (Chair of C-ROC) Tracey Wilkinson (Chair of HTOC)

# Document history

## Document version log

The table below summarise the changes made to this document compared to its superseded versions. For information on earlier versions not shown, please email the CRCT (crct@contacts.bham.ac.uk).

| Version | Reason for update |
| --- | --- |
| 3.0 (29-Jun-2026) | New SOP template, improving readability and updates to hyperlinks. In the background, added reference to ICH E3 Guidelines for Study Report writing for CTIMPs in Background section and reference to Human Medicine Regulation 2012 regarding the submission of study results to the MHRA within 6 months of trial end for in CTIMPs in paediatric populations. References to Project Set-up SOP and protocol templates/development tools removed. Guidance added to the Clinical Trials Tool Kit to differentiate between which forms are to be used to notify the end of a trial depending on the type of project (procedure 2.1). Added notification requirements to include contracted storage facilities and licensed tissue banks (procedure 4.1) and clarified post closure ethical scope for sample retention and use (procedure 5.1) Guidance added on deferrals and waivers regarding project transparency and updated contact details for CTIMPs when reporting that the trial results have been published to the review bodies (procedure 7.3). Updated reference to the EU clinical trials register (procedure 7.3). Added requirement for CTIMPs to provide a summary of the trial results to participants in an easy-to-understand manner (procedure 8.1). Terminology updates: ‘amendments’ change to ‘modifications’, ‘study/trial sites’ change to ‘study/trial locations’. Minor changes to grammar and updates to the abbreviations table. |

## Document revision log

The table below summaries the reason for any revisions made to the latest version of this document. Revisions do not affect the key content and/or requirements outlined in the document.

| Revision | Reason for revision | Editor/reviewer | Authoriser |
| --- | --- | --- | --- |
| - | - - | - | - |